FINDINGS OF FACT

May 4, 2026

# RECOMMENDATION FOR EXEMPTION FROM DESIGN-BID-BUILD, AUTHORIZE USE OF CONSTRUCTION MANAGER/GENERAL CONTRACTOR (CM/GC) ALTERNATIVE CONTRACTING METHOD FOR THE CHEMEKETA COMMUNITY COLLEGE WOODBURN CENTER HVAC UPGRADES PROJECT

Background

The Chemeketa Community College (CCC) Woodburn Center HVAC Upgrades (the “Project”) addresses a portion of the 2025 Bond project goals focused on replacement and modernization of aging mechanical systems across the Woodburn Center. The Woodburn Center HVAC Upgrades Project consists of complex mechanical system improvements, including full replacement of central plant equipment such as boilers and chillers, along with associated distribution systems, controls integration, and supporting infrastructure upgrades. The project will also include modernization of existing mechanical systems across occupied facilities to improve reliability, efficiency, and performance while maintaining continuous campus operations throughout construction.

On May 20, 2025, the voters of Marion, Linn, and Polk counties voted to pass bond measure 24-25-21 authorizing the sale of general obligation bonds in the amount of $140,000,000 to fund campus upgrades and enhancements such as:

Project Scope

Based on the bond language referenced above, a portion of the work consists of Woodburn Center HVAC work. This work is currently identified by Chemeketa Community College as the Woodburn Center HVAC Upgrades Project that will specifically include the following:

- The total project budget is approximately $2.0 million, inclusive of design, construction, contingencies, and other soft costs. The anticipated construction budget is approximately $1.2 million, with the remaining funds allocated to professional services, permitting, project management, and contingency

- Project Overview – Chemeketa Community College voters approved a $140 million capital bond in May 2025 to address critical capital improvements across the College, including modernization of existing facilities, deferred maintenance, and replacement of aging building systems necessary to maintain safe and reliable campus operations.

The Woodburn Center HVAC Upgrades Project consists of complex mechanical system improvements, including full replacement of central plant equipment such as boilers and chillers, upgrades to hydronic distribution systems, building-level HVAC components, and integration with campus-wide building automation and controls systems. The project will also include associated electrical, structural, and infrastructure improvements required to support the new mechanical systems.

This work will occur within and adjacent to existing occupied facilities that must remain fully operational throughout construction. As a result, the project will require careful planning and coordination of system shutdowns, temporary systems, phased construction, and tie-ins to existing infrastructure to minimize disruption to operations.

The project is anticipated to include demolition of existing mechanical equipment, installation of new high-efficiency systems, upgrades to ventilation and air distribution systems, and commissioning of all new and modified systems to ensure proper performance. The improvements are intended to enhance system reliability, improve energy efficiency, reduce maintenance needs, and extend the useful life of facilities.

Due to the complexity of integrating new systems with existing infrastructure, the project will require a high level of coordination between the Owner, design team, and contractor, along with detailed preconstruction planning to address constructability, phasing, and operational impacts.

Construction Delivery Method Recommendation/Risks and Challenges Discussion

After an analysis of the various options of contract delivery such as the traditional Design-Bid-Build (Hard Bid) and alternative methods such as Design/Build (DB), CM/GC, Qual+Bid, Prequalification of a selected group of bidders, Integrated Project Delivery (IPD), etc. it was determined that CM/GC is the best approach to the Woodburn Center HVAC Upgrades Project.

Therefore, it is the recommendation of the project team to proceed with a CM/GC delivery method for construction of this project. While other methods were considered, there are several factors that add complexity to this project and therefore require a deeper level of commitment and understanding from the contractor and the Owner-Design-Construction Team as a whole.

From the onset of the project, the Owner has been very clear about the schedule constraints for the Woodburn Center HVAC Upgrades project. To mitigate this, extremely tight coordination between owner activities and construction must take place. This coordination must begin during the pre-construction phase so that a contractor has ample time to prepare an appropriate approach, as well as give the owner and design team feedback on potential impacts. Phasing of construction may also be needed to accommodate programs needs, or to avoid inclement weather where construction may be less feasible. A CM/GC contractor can plan those phases during the design period, which allows them to also schedule their staff who are best suited for each project type.

Example concepts on next page.

The Project will entail many challenges and require careful planning and coordination during the design and construction phases for effective and efficient completion. Robust budget and schedule controls are essential to the Project’s success. It will be important to utilize a construction firm with the following specific capabilities:

- Ability to provide a complete project within CCC’s budget.

- Requisite expertise in renovating existing structures

- Exemplary reputation for on-time delivery with an aggressive timeline

- Supervisory staff experienced with working in and around occupied facilities and tight schedules

- Phasing logistical experience with various college programs utilizing space needs

- Innovative approaches to unique opportunities and unforeseen conditions

- Understanding of the importance of an integrated project team to the Project’s success

- Experience working closely with architects and engineers

- Ability and commitment to advise CCC on the state of the current market and engage the local subcontracting community

# CM/GC ALTERNATIVE CONTRACTING METHOD

The default method of procurement under the Oregon Public Contracting Code is competitive bidding, where a project is bid after completion of design and the contract is awarded to the lowest bidder. ORS 279C.337, however, authorizes the use of the Construction Manager/General Contractor (CM/GC) alternative contracting process provided that the Board of Directors, acting as the Local Contract Review Board, approves an exemption from competitive bidding. Under the CM/GC contracting method:

- The contractor is solicited prior to completion of the design phase pursuant to a competitive request for proposals process where selection is based upon evaluation of factors relating to the experience and expertise of the contractor rather than low bid.

- The contractor works with the owner and architect to develop the final design with the goals of improved constructability and value engineering, which results in fewer change orders and the ability to expedite the construction schedule. Under the standard design/bid/build method, the design is completed before the project is bid and the contractor brought on board.

- At the end of the design phase, the owner and contractor negotiate and agree on a guaranteed maximum price (“GMP”) and the construction schedule for the construction phase of the project.

- Generally, execution of the GMP Amendment starts the construction phase of the project. Early work, such as site demolition and preparation and early procurement of long lead items can occur prior to completion of the design phase under an Early Work Amendment, which also helps to expedite the construction schedule as compared to the standard design/bid/build method.

- Selection of subcontractors by the CM/GC must be competitive and involve the college in final decision making

CM/GC is the commonly used alternative contracting method by local governments for complex projects such as major expansions, renovations, and remodels of existing facilities such as the Project.

# Requested Action

Grant a specific exemption from the competitive bid process for a general contractor to allow the use of the Construction Manager/General Contractor method for the

Woodburn Center HVAC Upgrades Project. The request is based upon the draft findings in Exhibit A, which addresses the statutory requirements for an exemption from competitive bidding.

Exhibit A

ORS 279C.335 Competitive bidding requirement:

- Subject to subsection (4)(b) and (c) of this section, the Director of the Oregon Department of Administrative Services, a local contract review board or, for contracts described in ORS 279A.050 (Procurement authority) (3)(b), the Director of Transportation may exempt a public improvement contract or a class of public improvement contracts from the competitive bidding requirement of subsection (1) of this section after the Director of the Oregon Department of Administrative Services, the Director of Transportation or the local contract review board approves the following findings that the contracting agency submits or, if a state agency is not the contracting agency, that the state agency that is seeking the exemption submits:

  - The exemption is unlikely to encourage favoritism in awarding public improvement contracts or substantially diminish competition for public improvement contracts.

The requested exemption will not encourage favoritism or substantially diminish competition. The College will utilize a competitive RFP process to select the CM/GC firm. That procurement is formally advertised with public notice and disclosure of the planned Alternative Contracting Method. Full competition will be encouraged, and all qualified contractors will be invited to submit a proposal. The award will be based upon an objective review and scoring of proposals by a qualified College review committee based identified selection criteria set forth in the RFP. Once selected, the CM/GC will select subcontractors via competitive bid process in accordance with ORS 279C.337. The process will therefore provide for vigorous competition and provide the opportunity for all interested large and small contractors to participate in the project.

(b) Awarding a public improvement contract under the exemption will likely result in substantial cost savings and other substantial benefits to the contracting agency or the state agency that seeks the exemption or, if the contract is for a public improvement described in ORS 279A.050 (Procurement authority) (3)(b), to the contracting agency or the public. In approving a finding under this paragraph, the Director of the Oregon Department of Administrative Services, the Director of Transportation or the local contract review board shall consider the type, cost and amount of the contract and, to the extent applicable to the particular public improvement contract or class of public improvement contracts, the following:

    - How many persons are available to bid;

Facilities staff regularly receive inquiries into working at CCC from qualified construction manager/general contractor firms of varied sizes. There have been many interested CM/GC firms on this project who have spoken to project team members over this last year and many of those are anticipated to respond to the RFP solicitation.

    - The construction budget and the projected operating costs for the completed public improvement;

- Target value GMP budget of $1.2M for construction and $2M overall project budget have been established and have been provided to the design team. The College carefully established the budget for the project to be funded within the general fund and discussed that funds must be utilized in the most efficient manner. Utilizing the CM/GC will allow the College to use CM/GC pre-construction services during the design phase. Tasks to be performed by the CM/GC during this period include scheduling, logistics planning, constructability review, cost estimating and value engineering. These services will allow for the project team to develop a design, project schedule and budget that make the best use of available funds.

    - Public benefits that may result from granting the exemption;

Key benefits of using the CM/GC method is the coordination between the varied Project elements, including coordination of interruptions to activities, including pathway and utility shutdowns. Including avoiding unplanned building-wide heating and cooling outages during construction and maintaining continuous building operations. During a CM/GC preconstruction phase the contractor will be performing exploratory destructive surveying of existing building conditions to help verify design and limit unknown conditions. This early investigative work helps identify potential unknown conditions and reduce the likelihood of costly change orders during construction. This service is non-existent in a hard-bid traditional method of contracting and would result in immediate change orders. Coordinated efforts between the elements will reduce burden on staff and minimize impacts to classroom activities, recreation spaces, and other student programs and will reduce change orders and limit delays during the construction phase. This benefits the public through cost savings, provides “guaranteed” costs, and therefore allowing the public tax dollars to be spent more efficiently. This is also more likely to result in timely delivery of the Project and can reduce the closure timeframe of public facilities.

Unlike traditional design/bid/build procurement, an RFP allows the College to review the resumes of the Project Manager, Superintendent, and Subcontractors who will make up the proposed general contractor’s project team, ensuring the selected firm(s) has experience and expertise in this type of complicated, interrelated project on an operating campus site.

    - Whether value engineering techniques may decrease the cost of the public improvement;

Value engineering provided by a single Construction Manager should optimize trade production while on site and tighten the overall time frame of construction duration. Due to the proximity of construction zones of the varied elements, a Construction Manager looking at the time of implementation may suggest adjustment of scope between elements to better align with phasing of adjacent work. The resequencing of work to align Project scope and optimize utilization of trade labor is a significant advantage of the CM/GC contract approach for this project group. The CM/GC delivery method also allows for the general contractor and subcontractors with specialized expertise and common project goals to participate in the value engineering process during the design phase, to work with the Owner and Design Team to evaluate and select true alternatives of comparable quality not simply reduce cost with value diminishment. This will also result in a more effective and efficient process as compared to value engineering by change order to a completed design.

    - The cost and availability of specialized expertise that is necessary for the public improvement;

Completing a complex school project on time, within budget, and in full compliance with construction documents and specifications requires the CM/GC firm to dedicate a qualified team with the experience and expertise to work collaboratively with the college, architects, engineers, and the project management team. Including expertise in central plant systems (boilers and chillers), building automation systems (BAS/DDC), and complex system integration with existing infrastructure. The collaborative process is expected to reduce or eliminate rework and minimize disruptions to ongoing college activities and surrounding communities. The Request for Proposals (RFP) process used to select the CM/GC firms will enable the College to select the best contractor for the project.

The RFP process allows for review of contractor expertise not afforded in traditional procurement. The Project is complex and requires a general contractor with specialized expertise due to the complexities of the campus, including:

- Executing the Project with the least disruption to critical campus safety operation.

- Cooperation and coordination with multiple consultants and contractors on this and other projects.

- Complex Phase logistics between college programs and needed spaces during construction

    - Any likely increases in public safety;

The CM/GC firm will be required to prepare a comprehensive project safety plan to ensure construction activities are performed safely while minimizing impacts to the Center and surrounding neighborhood. Because the project is located within an active institutional environment, selecting a contractor with experience working on occupied educational facilities will be critical to maintaining public safety and coordinating construction activities with ongoing operations. Early involvement of the CM/GC during the design phase will allow the contractor to fully understand the project’s complexities, schedule constraints, and operational impacts so the safety plan can address these factors effectively. Construction will also require ongoing coordination of safety barricades, work zones, and egress paths as work progresses to maintain safe access and minimize disruption to college activities.

    - Whether granting the exemption may reduce risks to the contracting agency, the state agency or the public that are related to the public improvement;

The CM/GC process will mitigate risks as described above and listed below:

- Risk of unplanned system outages during tie-ins

- Need for temporary heating/cooling during system replacement

- Unknown conditions in existing mechanical infrastructure

- Site coordination.

- Site staging and laydown coordination.

- Site safety and work hours.

- Use of a highly qualified renovation team.

- The establishment of the GMP will provide a complete project within CCC’s budget.

- CM/GC contracting allows for CCC to engage in early work agreements that give more insight and site verification of unforeseen conditions to the architects, contractors, and CCC, as well as expedite the construction schedule by starting early work during the design phase.

- Prior to the establishment of the GMP, the CM/GC will provide collaborative cost alignment during the reconciliation process with real-time cost information in conjunction with Design Team and a third-party Cost Estimation Team.

    - Whether granting the exemption will affect the sources of funding for the public improvement;

This project is to be funded with proceeds from the 2025 general obligation bond proceeds. The contracting method has no impact on the funding source.

    - Whether granting the exemption will better enable the contracting agency to control the impact that market conditions may have on the cost of and time necessary to complete the public improvement;

Because the CM/GC process appoints the general contractor early into the design, CCC takes advantage of market prices by facilitating early purchase of certain project elements, if needed. The construction manager can also seek the help of specialized subcontractors regarding information about specific equipment needs and gain advanced notice of when price increases are expected. This allows CCC to make better informed decisions and reduce the risk of acting prematurely or reacting too late. The preconstruction efforts of a construction manager should also help to explore alternative suppliers of equipment and materials along with alternative construction methods to react to changing market conditions and control project costs.

    - Whether granting the exemption will better enable the contracting agency to address the size and technical complexity of the public improvement;

The Project is very complex, and the work will be spread out in various areas, rather than focusing work on a single, isolated area. A construction manager can forecast the shifting needs of construction and better predict the schedule, allowing CCC to communicate more effectively with campus programs. The Project requires integration of new central plant equipment with existing systems, phased replacement of active HVAC systems, and coordination of building automation systems across multiple facilities while maintaining continuous operations. Having a single construction manager for this group of project elements will minimize the need for CCC staff to coordinate various trade activities between scopes and instead focus on coordination of projects with campus entities.

    - Whether the public improvement involves new construction or renovates or remodels an existing structure;

The project scope is renovation of existing structures within and around the Woodburn Center area, reference campus map in Project Scope section above. Procuring a contractor with experience in complex Mechanical and renovation on a live learning academic setting is critical.

    - Whether the public improvement will be occupied or unoccupied during construction;

The construction will occur in existing structures and in close proximity to existing facilities. An intense and well thought out safety and coordination plan must be implemented to ensure members of the public, staff members, and students are kept safe and instructional activities are not disrupted. Utilizing the CM/GC process will allow the College to select a contractor who has the sensitivity and experience to safely and successfully work in close proximity and in direct coordination with ongoing activities.

    - Whether the public improvement will require a single phase of construction work or multiple phases of construction work to address specific project conditions; and

The project phasing and logistics will most likely require multiple complex and specialized construction phasing. The preconstruction period required by the CM/GC method of contracting allows careful study, analysis and planning to ensure minimal disruption in construction to occupancy overlapping to minimize disruptions. Other project elements may combine phases or be best executed in conjunction with standalone phasing scopes.

    - Whether the contracting agency or state agency has, or has retained under contract, and will use contracting agency or state agency personnel, consultants and legal counsel that have necessary expertise and substantial experience in alternative contracting methods to assist in developing the alternative contracting method that the contracting agency or state agency will use to award the public improvement contract and to help negotiate, administer and enforce the terms of the public improvement contract.

Current facilities management, retained consultants, and bond staff have successfully developed project management tools and executed many CM/GC projects to substantial completion on past bond measures on campus for CCC and other community colleges in Oregon. This same staff and tool set will be used for the Woodburn Center HVAC Upgrades Project.

CCC has used this alternative contracting method on the following projects: The Agricultural Science Building Project in 2020 utilized CM/GC, Health Science Complex in 2008 and Yamhill Valley Campus in 2010 both utilized CM/GC successfully. Currently CM/GC is being utilized for the Building 7 renovation project and the Trade Center.

CCC’s project management consultant, R&C Management Group, has extensive experience with the CM/GC alternative contracting method and with utilization of the CM/GC contracting on community colleges and other public-body construction projects throughout Oregon.

The above findings addressing ORS 279C.335(2)(b)(A)-(N) fully consider the information as required under “Findings” defined, 279C.330(1)(a)-(h).

Based upon the analysis above, granting the exemption will likely result in substantial cost savings and other substantial benefits to CCC.

# CONCLUSION

For the reasons stated above, the draft findings support an exemption from competitive bidding under ORS 279C.335 to utilize the CM/GC alternative contracting process for the Woodburn Center HVAC Upgrades Project.